## PLANTA PUERTO MALDONADO
FORMATO N°17
PETROPERÚ S.A. - FICHAS DE PROYECTOS DE INVERSIÓN
CONSTRUCTION OF SALES PLANT IN PUERTO MALDONADO
1. Description
Consists of the construction of a Sales Plant in the department of Madre de Dios, with a storage capacity of 50 MB, for the dispatch of Diesel B5 and gasoline.
2. Components of the investment
• Civil and sanitary works. • Metalworks. • Fire fighting system. • Equipment for service isles. • Office furniture and equipment.
3. Funding source
PETROPERÚ S.A. own resources.
4. Physical and Financial Progress as of Q IV
Components | Financial Progress (M S/) |  |  |  | Physical Progress3 (%)
| Total Investment 1 | Cumulative execution | Budget Year 20242 | Execution Year 2024 | Scheduled for Quarter I | Actual by Quarter I
Engineering and previous procedures | 1300 | 1699 | - | - | - | -
Land | 733 | 733 | - | - | - | - | inv total IP | 65196.558
Materials, equipment and works | 63164 | 62732.6881 | 0 | 0 | 66.6 | 59.7
Total | 65197 | 65164.6881 | 0 | 0 | 66.6 | 59.7 | ACUM AL 2023 | 65164.6881 | 62732.6881
1 Investment amount approved with A/D No.120-2018-PP of 20.12.2018. It is currently being updated. | [6 empty] | EJEC A MAR 2024 | 0
2 Approved with A/D No. 0166-2023-PP on 14.12.2023. | [7 empty] | 65164.6881
3 According to the baseline review of the project carried out in September 2023.
5. Main activities carried out and current situation
- The project is under re-evaluation considering the need to include additional components, such as: external drainage system, access road, among others. Currently, the detailed engineering development service is in the process of contracting, in order to obtain the new CAPEX of the project. - With regard to the progress of the procurement and construction service, coordination is carried out with the contractor TECNITANQUES Ingenieros S.A.S., in order to resolve by mutual dissent Contract No.4100008911 "Procurement and Construction Service of the New Puerto Maldonado Supply Plant" on pause since 01.01.2022.